## Gantt Chart
Project Task | Span | AUTUMN SEMESTER (Weeks 1–15) | [6 empty] | SPRING SEMESTER (Weeks 16–30)
General Task Activity | Weeks | W1–2 | W3–4 | W5–6 | W7–8 | W9–10 | W11–12 | W13–15 | W16–18 | W19–20 | W21–22 | W23–24 | W25–26 | W27–28 | W29–30
1. Setup environment & Docker | W1–W3 | ■ | ■
2. Simulate world, actors & baseline | W3–W6 |  | ■ | ■
3. Prepare obstacle tracker (vision + LiDAR) | W7–W12 |  |  |  | ■ | ■ | ■
4. Setup automated testing harness | W8–W18 |  |  |  | ■ | ■ | ■ | ■ | ■
5. Develop predictive navigation controller | W13–W18 | [6 empty] | ■ | ■
6. Run comparative simulation benchmarks | W19–W24 | [8 empty] | ■ | ■ | ■
7. Analyze results & statistical metrics | W22–W26 | [9 empty] | ■ | ■ | ■
8. Write final thesis & prepare video demos | W25–W30 | [11 empty] | ■ | ■ | ■

## Task Breakdown
Semester | Weeks | General Task Description | Hours | Key Deliverable & Milestone
Autumn Semester | W1–W3 | 1. Setup environment & Docker | 45 h | Ubuntu 24.04, ROS 2 Jazzy, Gazebo Harmonic & reproducible Docker container ready.
Autumn Semester | W3–W6 | 2. Simulate world, actors & baseline | 45 h | Indoor corridor world, moving obstacle actors, and C0 range-only baseline logged.
Autumn Semester | W7–W12 | 3. Prepare obstacle tracker (vision + LiDAR) | 90 h | Multi-modal tracker (O1) publishing smoothed obstacle positions and velocities.
Autumn / Spring | W8–W18 | 4. Setup automated testing harness | 45 h | Parallel scenario spawner, automated trial runner, and metric logger ready.
Autumn / Spring | W13–W18 | 5. Develop predictive navigation controller | 75 h | Closed-loop predictive MPPI critic (O2) running at ≥ 20 Hz alongside C1 baseline.
Spring Semester | W19–W24 | 6. Run comparative simulation benchmarks | 60 h | Batch simulation trials completed across C0, C1, and C2 under varying speeds/densities.
Spring Semester | W22–W26 | 7. Analyze results & statistical metrics | 30 h | Statistical comparisons (t-test / ANOVA), performance plots, and stretch profiling.
Spring Semester | W25–W30 | 8. Write final thesis & prepare video demos | 60 h | Final MEng dissertation report, documented source code, and simulation video demos.