The University of Nottingham

Faculty of Science and Engineering

Department of Electrical and Electronic Engineering

EEEE4077 Mechatronics Project

Project Outline and Planning Report

Vision-Augmented Mobile Robot Navigation in Dynamic Environments

AUTHOR		:	Nicholas Khor Han Le

ID			:	20617556

SUPERVISOR	:	Dr. Shalini Darmaraju

MODERATOR	:	Ir Dr. Daniel Pu

DATE			:	28 October 2026

Table of Contents

1. Overview of the Project	3

1.1 Commercial Context and the Freezing Robot Bottleneck	3

1.2 Project Aim and Core Objectives	3

1.3 System Architecture, Component Requirements, and Dependencies	4

2. Specification	4

3. Methodology	6

3.1 Development Lifecycle, Student Skill Assessment, and Tool Limitations	6

3.2 Algorithmic Synthesis and Interdependency Analysis	6

4. Originality	7

4.1 Multifaceted Novelty in Deliverable, Architecture, and Development Approach	7

4.2 Acknowledged Project Limitations and Quantified Impact on Specification	8

5. Risk Management	8

6. Planned Work Schedule	9

References	11

Appendix A: Supervisor-Provided Project Specification	12

A.1 Project Description	12

A.2 Target Sustainable Development Goals (SDGs)	12

A.3 Project Objectives	12

A.4 Project Deliverables & Resource Breakdown	12

# 1. Overview of the Project

## 1.1 Commercial Context and the Freezing Robot Bottleneck

According to the International Federation of Robotics (IFR), transportation and logistics represented the largest commercial application class for professional service robots in 2024, recording 102,900 unit deployments globally—a 14% year-on-year expansion [1]. The vast majority of these Autonomous Mobile Robots (AMRs) operate in brownfield industrial facilities: pre-existing warehouses, distribution hubs, and manufacturing shop floors that cannot be rebuilt around segregated automated lanes. Instead, AMRs must navigate narrow corridors shared with dynamic human workers, pallet jacks, and forklifts. To maintain commercial cost viability and adhere to industrial functional safety standards (ISO 3691-4 / SIL-2), brownfield AMRs predominantly pair a single-plane (2D) safety laser scanner with the open-source Robot Operating System 2 (ROS 2) Navigation stack, Nav2 [2], [3]. While planar 2D LiDAR provides millimetre-accurate Time-of-Flight (ToF) ranging over wide horizontal fields of view (270°–360° at 20–40 Hz), coupling planar range sensing with standard 2D occupancy grids (nav2_costmap_2d) introduces a critical operational bottleneck in dynamic environments: the Freezing Robot Problem [4].

Formally identified by Trautman and Krause [4], the freezing robot problem occurs when an autonomous mobile robot navigating amidst moving traffic halts, oscillates, or executes erratic recovery spins because its planner evaluates all forward trajectories as unsafe:

•  Planar Point Fragmentation and Semantic Blindness: A 2D LiDAR mounted 10–20 cm above the floor intersects a walking pedestrian as two sparse, oscillating point clusters (lower-limb cross-sections) lacking semantic class identity, volumetric bounds, or velocity vectors.

•  Time-Invariant Occupancy Representation (t = 0): Standard Nav2 pipelines insert laser scans directly into nav2_costmap_2d [2], modeling every occupied cell as an immovable static barrier fixed at time t = 0. When a pedestrian crosses a corridor 3 m ahead at a nominal walking speed of 1.2–1.4 m/s [9], the controller cannot project that the agent will vacate the aisle within 1.0–1.5 s. All forward candidate trajectories accumulate severe obstacle costs, collapsing the velocity command to zero. Furthermore, projecting 3D camera points directly into the 2D costmap worsens freezing because raycasting decay latencies leave lingering 'phantom clearing trails'.

## 1.2 Project Aim and Core Objectives

Project Aim: To design, implement, and systematically evaluate in simulation an open-source ROS 2 navigation framework that fuses monocular camera visual tracking with planar 2D LiDAR range measurements to estimate moving obstacle positions and velocities, and incorporates short-term motion predictions into a native Nav2 Model Predictive Path Integral (MPPI) trajectory critic to eliminate robot freezing in dynamic environments.

In strict compliance with supervisor specification SD-MEng-26-01 (Hardware 0% / Software 60% / Research 40%), the project focuses on three core objectives: (O1) Multi-Modal Dynamic Obstacle Tracker—adapting YOLOv8n detection and two-stage 2D ByteTrack association [8] in image space, fused with planar 2D LiDAR via Zhang–Pless extrinsic calibration [6] and frustum median depth gating into a per-track Constant-Velocity (CV) Linear Kalman Filter [7] estimating [x, y, vx, vy]^T; (O2) Predictive Dynamic MPPI Controller—developing a native C++17 pluginlib critic (DynamicObstaclesCriticPlugin) inside nav2_mppi_controller [5], [10] that forward-projects obstacle states across the lookahead horizon (τ ∈ [0, 2.0] s) with time-expanding Gaussian safety buffers; and (O3) Systematic 3-Way Comparative Ablation—benchmarking the system in Gazebo Harmonic across varying obstacle speeds (0.5–2.0 m/s), crossing geometries, and agent densities (1–4 agents) across configurations C0 (2D LiDAR baseline), C1 (Vision detection only at t = 0), and C2 (Full predictive MPPI).

## 1.3 System Architecture, Component Requirements, and Dependencies

Figure 1 illustrates the system architecture, decoupling static infrastructure (retained in nav2_costmap_2d) from moving obstacles (routed through the O1 state-space tracker to the O2 predictive critic). Table 1 details the component-level design requirements, API/message interfaces, execution latency budgets, and physical limitations. Dependencies run sequentially from left to right: the MPPI critic relies on low-jitter velocity vectors from the Kalman filter, which depends on accurate frustum median depth gating anchored to persistent 2D ByteTrack identities.

Figure 1. System architecture block diagram showing subsystem boundaries, ROS 2 interfaces, operating rates, and data dependencies.

Table 1. Component-level design requirements, ROS 2 interfaces, execution latency budgets, and limitations.

| Subsystem Component | Input → Output Interface & Data Type | Rate / Latency Budget | Critical Design Requirement & Algorithmic Limitation |
| --- | --- | --- | --- |
| 2D Object Detector (YOLOv8n) | sensor_msgs/Image (1280×720) → 2D boxes B_i = [u_min, v_min, u_max, v_max], score s_i, class | ≥ 30 Hz (12–18 ms FP16 TensorRT) | Must exceed LiDAR scan frequency. Limited to trained classes (Pedestrian, Forklift, Cart); confidence drops under motion blur. |
| 2D MOT Tracker (ByteTrack [8]) | 2D detections (B_i, s_i) → active tracks with persistent integer track_id | ≥ 30 Hz (1–2 ms CPU Hungarian IoU) | Two-stage association (θ_high=0.6, θ_low=0.1) bridges partial visual occlusions up to N_lost = 30 frames (1.0 s). |
| Extrinsic Frustum Gating [6] | Active 2D tracks + sensor_msgs/LaserScan → metric Cartesian observation z_k = [x_m, y_m]^T | Per scan (20–40 Hz, 1–2 ms vectorized) | Projects laser via λ[u, v, 1]^T = K[R¦t][X_L, Y_L, 0, 1]^T. Median filter rejects background wall bleed-through; limited to overlapping 80° FOV. |
| Per-Track Linear Kalman Filter [7] | Metric cluster z_k → /tracked_obstacles (state x_k = [x, y, vx, vy]^T, covariance P_k) | 30 Hz (< 0.2 ms Eigen3 C++ matrix ops) | Constant-Velocity (CV) model with Mahalanobis gate (d_M^2 < γ). Valid over short horizons (T ≤ 2.0 s) [9]; lags on abrupt turns. |
| MPPI Dynamic Critic Plugin [5], [10] | /tracked_obstacles + M=2000 rollouts (N=40 steps, Δt=0.05 s) → trajectory cost tensor | ≥ 20 Hz controller (< 0.3 ms SIMD C++17) | Evaluates p_obs(τ_k) = p_0 + v_obs·τ_k with expanding Gaussian buffer σ_i(τ_k) = R_rob + R_obs + α·τ_k. Static walls stay in costmap_2d. |

# 2. Specification

All project requirements are formulated as SMART quantitative hypotheses evaluated in software simulation (Table 2). Each numeric requirement specifies a Minimum threshold (baseline pass criterion) and an aspirational Target (research goal). Evaluation in Gazebo Harmonic covers five standardized indoor scenarios across obstacle speeds of 0.5–2.0 m/s and densities of 1–4 agents: (A) perpendicular corridor pedestrian crossing, (B) head-on oncoming pedestrian in a narrow aisle, (C) higher-speed manual cart crossing, (D) multi-agent intersection (2–4 pedestrians), and (E) static obstacle control. Three configurations (C0 Range-only baseline, C1 Vision detection at t = 0 without velocity prediction, and C2 Full predictive MPPI) are compared across ≥ 30 paired trials per scenario using shared pseudo-random seeds.

Table 2. Project specification, quantitative hypotheses, literature justification, test criteria, and challenge level (L/M/H).

| ID | Specification Requirement | Minimum | Target | Engineering & Literature Justification | Test Method & Success Criterion | Ch. |
| --- | --- | --- | --- | --- | --- | --- |
| O1-a | Obstacle velocity RMSE (≤ 8 m range) | < 0.25 m/s | < 0.15 m/s | ≈ 10% of nominal 1.4 m/s walking speed [9]; bounds 2.0 s horizon projection error to < 0.3 m. | Velocity RMSE of /tracked_obstacles vs. Gazebo actor ground-truth /tf over ≥ 30 runs. | M |
| O1-b | Camera–LiDAR frustum association | ≥ 85% | ≥ 95% | Accurate ray gating [6] prevents background wall range spikes from corrupting KF covariance [7]. | % of visual detections assigned a gated laser cluster within 0.3 m of ground-truth centroid. | M |
| O2-a | Controller freezes per 10 crossings | ≥ 50% below C0 | 0 freezes | Directly resolves the freezing robot problem [4] where static costmap critics halt or spin. | Count controller timeouts, recovery triggers, and stationary halts (¦v¦ < 0.05 m/s for > 2.0 s). | H |
| O2-b | Mean route completion time vs. C0 | ≥ 10% shorter | 15–25% shorter | Proactive speed modulation and wake-passing eliminate stop-and-restart intersection delays. | Paired comparison of mean transit time ± 95% CI across ≥ 30 seeded runs per scenario. | M |
| O2-c | Collision-free navigation (Hard rule) | 0 collisions | 0 collisions | Predictive yielding must never compromise physical collision safety (ISO 3691-4 principle). | Monitored continuously via Gazebo physics contact sensors; any contact fails the trial. | M |
| O3-a | 3-Way Ablation separation (C0/C1/C2) | p < 0.05 | p < 0.01 | Isolates whether gains stem from visual identification (C1) or motion prediction (C2). | Paired Welch's t-test and one-way ANOVA across 30 runs/scenario across speeds (0.5–2.0 m/s). | M |
| O3-b | Cumulative waiting time per run | ≥ 50% reduction | ≤ 5.0 s | Quantifies reduction in intersection deadlocks during dynamic cross-traffic encounters. | Integrate total duration where linear speed ¦v¦ < 0.05 m/s while navigation goal is active. | M |
| O3-c | End-to-end control & tracker rate | ≥ 15 Hz | ≥ 20 Hz | Controller must match planar LiDAR scan rate (20 Hz) for real-time trajectory generation [10]. | Sustained mean execution frequency of tracker (≥ 30 Hz) and MPPI (≥ 20 Hz) over 5-min runs. | L |
| NF1 | Containerized reproducibility | Pass | Pass | Enables moderator and future work to deterministically reproduce all benchmark results. | Single ROS 2 launch file inside a pinned Docker container regenerates raw logs and tables. | L |

Stretch Goals, Deliverable Mapping, and Attainability: Table 3 defines prioritized stretch goals (S1–S3) alongside deliverable mappings and assessment criteria for each objective. All work runs in simulation on an available workstation (NVIDIA RTX 4070 Ti Super GPU, multi-core CPU) within the 450-hour budget (Section 6), requiring zero hardware lead time while achieving predictive avoidance beyond COTS static-costmap AMRs.

Table 3. Prioritized stretch goals (S1–S3) and objective-to-deliverable assessment mapping (O1–O3).

| ID / Obj. | Stretch Goal or Tangible Software Deliverable | Trigger Condition / Concrete Artifact | Assessment Method & Validation Criterion |
| --- | --- | --- | --- |
| S1 (Stretch) | Dense Crowd Stress Benchmark (4–6 interacting agents) | Triggered if O1 & O2 meet Target metrics by Review 3 (W18). | Evaluate ByteTrack ID persistence and MPPI non-convex rollout scoring under dense occlusion. |
| S2 (Stretch) | High-Speed (2.5 m/s) & Oblique Crossing Angles (30°, 45°, 135°) | Triggered if Scenarios A–E complete ahead of Week 22. | Quantify kinematic breakdown boundaries of the Constant-Velocity (CV) filter. |
| S3 (Stretch) | Embedded CPU-Only Resource Profiling (4-core cgroups limit) | Triggered if Phase D finishes with spare compute margin. | Verify ≥ 20 Hz MPPI loop rate without discrete edge GPU acceleration. |
| O1 Deliv. | Multi-Modal Dynamic Tracker (lidar_vision_tracker package) | YOLOv8n + ByteTrack + Zhang–Pless gate + Linear KF node. | Verified against Gazebo /tf ground truth across ≥ 30 runs (O1-a < 0.15 m/s, O1-b ≥ 95%). |
| O2 Deliv. | Predictive MPPI Critic (nav2_mppi_dynamic_critic package) | C++17 DynamicObstaclesCriticPlugin + Fallback F1 layer. | Closed-loop crossings verifying O2-a (0 freezes), O2-b (15–25% faster), O2-c (0 collisions). |
| O3 Deliv. | 3-Way Ablation Suite & Final MEng Dissertation | Gazebo scenario runner, rosbag2 logger, scipy stats scripts. | Paired Welch's t-test / ANOVA (p < 0.01) across C0, C1, C2 + reproducible video demos. |

# 3. Methodology

## 3.1 Development Lifecycle, Student Skill Assessment, and Tool Limitations

The project executes a quantitative, simulation-based engineering methodology partitioned into six sequential steps (M0–M5, Table 4). Each step is assessed against the student's existing skill set (established competency in Python, C/C++, state-space control, and basic ROS 2 workspaces, with Nav2 C++ pluginlib internals identified as the primary learning curve) and explicitly accounts for tool limitations and familiarization tasks.

Table 4. Development lifecycle steps (M0–M5), tools, limitations, student skill challenge, and additional familiarization tasks.

| Step | Core Process & Selected Tools | Tool Limitations & Project Impact | Student Challenge & Additional Familiarization Tasks |
| --- | --- | --- | --- |
| M0: Env | Ubuntu 24.04 LTS, ROS 2 Jazzy Jalisco, Gazebo Harmonic, Docker + NVIDIA Toolkit. | ROS 2 Iron is EOL (2024); Humble reaches EOL in May 2027. WSL2 can add GPU/GUI overhead vs. native Linux. | Challenge: Medium. Student has ROS 2 CLI/node foundations. *Extra task:* W1 spike comparing native dual-boot vs. WSL2 GPU passthrough; freeze Dockerfile. |
| M1: Sim & C0 | Gazebo Harmonic corridor world, diff-drive AMR URDF, scripted actors, nav2_bringup. | Scripted actors follow deterministic paths unless randomized; physics contact checks require explicit collision sensors. | Challenge: Medium. *Extra task:* Build modular SDF actor spawners with seeded speed (0.5–2.0 m/s) & phase offsets; freeze and log C0 baseline first. |
| M2: Tracker (O1) | Python/C++ node, YOLOv8n, boxmot (ByteTrack [8]), OpenCV/Eigen3 projection [6], KF [7]. | Camera FOV (80°) is narrower than LiDAR (360°); laser rays bleed past narrow legs onto background walls. | Challenge: Medium. *Extra task:* Implement frustum median depth clustering and Chi-square Mahalanobis gating (d_M^2 < γ) to reject background wall hits. |
| M3: Critic (O2) | Native C++17 mppi::critics::CriticFunction plugin (pluginlib) in nav2_mppi_controller [10]. | Highest Technical Risk: Unvectorized C++ batch evaluation across 80,000 states/cycle can breach the 50 ms (20 Hz) budget. | Challenge: High (first Nav2 C++ plugin). *Extra task:* Write minimal 'Hello-Critic' plugin in Week 8 to master pluginlib exports and SIMD tensors early. |
| M4: Harness (O3) | Automated Python launch runner, Gazebo services, rosbag2 recorder, /tf comparator. | Batch execution (3 configs × 5 scenarios × 30 runs = 450 trials) can hang if Gazebo or Nav2 lifecycle nodes fail to reset. | Challenge: Medium. *Extra task:* Implement watchdog process timeouts, deterministic seed injection, and headless Gazebo server execution (-s). |
| M5: Analysis (O3) | Python post-processing suite (numpy, scipy.stats, matplotlib). | Unpaired or small sample sizes (N < 30) yield under-powered p-values under multi-agent trajectory variance. | Challenge: Low. *Extra task:* Automate paired Welch's t-test, one-way ANOVA, and 95% CI plotting directly from recorded MCAP bags. |

## 3.2 Algorithmic Synthesis and Interdependency Analysis

Candidate algorithms across perception, motion prediction, and local control were selected via parametric trade-off analysis (Table 5) to guarantee real-time determinism (20 Hz control loop) on standard CPU hardware. Figure 2 shows the task interdependency graph: M0 → M1 → M2 → M3 → M5 forms the critical path because closed-loop tuning of the MPPI dynamic critic (M3) requires live velocity tracks from M2, which requires the M1 simulation world. Developing the ablation harness (M4) in parallel after M1 decouples test infrastructure from tracker/controller delays, while Fallback F1 (velocity-inflated costmap layer) protects M5 if M3 encounters C++ linking hurdles at the Week 8 spike.

Table 5. Algorithmic trade-off synthesis across tracking, motion prediction, and local trajectory optimization.

| Subsystem | Selected Method & Complexity | Evaluated Alternatives | Quantitative & Architectural Synthesis Justification |
| --- | --- | --- | --- |
| 1. Association & Depth (O1) | 2D ByteTrack [8] + Frustum Gate [6] O(N·M) IoU + O(M³) Hungarian; < 3 ms CPU. | • *2D Laser Clustering:* O(P log P) • *DeepSORT:* CNN ReID per box • *PointPillars 3D:* > 30 ms GPU | Laser clustering fragments during leg-crossings, causing velocity spikes. PointPillars/DeepSORT demand heavy GPU VRAM. ByteTrack solves occlusion-resilient association in 2D pixel space (< 2 ms CPU), while frustum median gating extracts exact ToF depth without stereo noise (ΔZ ∝ Z²). |
| 2. Motion Model (O1/O2) | Discrete Linear KF (Constant Velocity [7], [9]) p_obs(τ) = p_0 + v_obs·τ; O(1)/track (< 0.01 ms). | • *Social Force (SFM) [9]:* O(K²) • *Interactive GP (IGP) [4]:* O(K³) • *Traj. Transformers:* O(L²) GPU | Helbing & Molnar [9] showed pedestrian speeds (1.2–1.4 m/s) exhibit strong directional inertia over short intervals. Across 80,000 rollout queries/cycle (M=2000 × N=40), SFM, IGP, or neural predictors exceed the 50 ms budget. Linear CV propagation is closed-form, SIMD-vectorizable, and accurate for T ≤ 2.0 s. |
| 3. Trajectory Control (O2) | Nav2 MPPI + Dynamic Critic [5], [10] M=2000 rollouts, T=2.0 s, Δt=0.05 s; < 15 ms CPU. | • *Dynamic Window (DWA):* T ≤ 1.0 s • *Timed Elastic Band (TEB):* g2o • *SE-MPPI QP-CBF [11]:* post-filter | DWA samples constant (v,ω) arcs and freezes at crossings. TEB suffers local minima when multiple dynamic agents cross. Injecting spatio-temporal Gaussian cost L_dyn = Σ w_dyn·exp(-¦¦p_rob(τ_k) - p_obs,i(τ_k)¦¦² / 2σ_i²(τ_k)) into MPPI reshapes the rollout distribution in < 0.3 ms on CPU. |

Figure 2. Methodology interdependency graph showing the critical path (red solid), parallel harness workstream (blue dashed), and Risk R2 fallback (red dotted).

# 4. Originality

## 4.1 Multifaceted Novelty in Deliverable, Architecture, and Development Approach

While planar camera–laser calibration [6], 2D ByteTrack association [8], Kalman filtering [7], and path-integral control [5] exist as isolated components, a clear architectural gap separates low-cost brownfield warehouse AMRs from compute-intensive academic SOTA navigation (Table 6). This project demonstrates multifaceted originality across four dimensions:

•  Idiomatic Open-Source Architectural Extension: Direct inspection of the production ROS 2 nav2_mppi_controller codebase confirms that all 11 shipped critics evaluate obstacle costs strictly against static 2D costmaps at t = 0 [10]. Developing a native C++17 mppi::critics::CriticFunction plugin that forward-projects obstacle trajectories (p_obs(τ_k) = p_0 + v_obs·τ_k) with time-expanding uncertainty radii (σ_i(τ_k) = R_rob + R_obs + α·τ_k) resolves controller freezing while preserving standard Nav2 Behavior Trees and static costmaps.

•  Low-Cost Brownfield Sensor Complementarity: Retrofitting a deployed 2D safety LiDAR (≈ $400) with a $30–$50 monocular camera (≈ $450 total suite vs. > $3,000 for 3D LiDARs [1]) translates 2D optical association and planar ToF laser ranging into a late-fusion observer free of monocular scale drift and quadratic stereo depth error.

•  Differentiation from 2024–2025 Academic MPPI Frontiers: Recent MPPI variants target orthogonal problems using heavy GPU compute: SE-MPPI (Kang, 2024 [11]) applies a reactive QP Control Barrier Function post-filter to u_0 without reshaping multi-second rollout horizons; EXACT-MPPI (Peng et al., 2024 [12]) computes continuous Signed Distance Functions from raw point clouds via JAX CUDA kernels on GPU, treating obstacles as static geometry; and CSC-MPPI (RCILab, 2025 [13]) relies on GPU cuML DBSCAN clustering to avoid symmetric mode-averaging collapse. In human cross-traffic, however, the obstacle's velocity vector v_obs naturally breaks spatial symmetry—penalizing future positions automatically skews rollouts into the pedestrian's trailing wake in < 0.3 ms on standard CPU SIMD instructions without GPU clustering.

•  Originality in Experimental Methodology (3-Way Ablation): Unlike monolithic navigation benchmarks, our 3-way ablation (C0 vs. C1 vs. C2) rigorously isolates spatial visual bounding (t = 0) from temporal velocity extrapolation (τ ∈ [0, 2.0] s).

Table 6. Differentiation from current industrial practice, tracking pipelines, and 2024–2025 academic SOTA MPPI frontiers.

| Dimension | Industrial Baseline (Stock Nav2 + 2D LiDAR [2]) | Vision–LiDAR Trackers (Without Predictive Critic) | Academic SOTA MPPI (SE [11], EXACT [12], CSC [13]) | This Project (Proposed Brownfield Framework) |
| --- | --- | --- | --- | --- |
| Sensor Suite & Cost | Planar 2D LiDAR (≈ $400) | 2D/3D LiDAR + RGB/Stereo ($500–$4,000) | 3D LiDAR / Depth Point Clouds (> $3,000) | 2D LiDAR + Monocular RGB Retrofit (≈ $450) |
| Obstacle Model | Unclassified 2D costmap cells fixed at t = 0 | Tracked boxes injected into static 2D costmap | Unsegmented SDF point clouds [12] or t=0 barriers [11] | Decoupled: Static costmap + metric tracks [x,y,vx,vy]^T |
| Rollout Scoring | 11 static costmap critics (t = 0) → Freezes | Static clearance inflation (t = 0) + raycast trails | JAX GPU SDF rollouts [12], cuML DBSCAN [13], QP-CBF [11] | Native C++ MPPI Critic (p_0 + v_obs·τ_k, expanding σ) |
| Compute Budget | Standard onboard CPU | CPU + Edge GPU | Dedicated CUDA GPU VRAM (JAX / RAPIDS cuML) | Standard CPU for control (< 0.3 ms SIMD); light detector |
| Validation Design | Ad-hoc static obstacle tests | Isolated MOTA / tracking RMSE metrics | Monolithic benchmark against legacy DWA/TEB | Controlled 3-way ablation (C0 vs C1 vs C2) across speeds |

## 4.2 Acknowledged Project Limitations and Quantified Impact on Specification

•  Simulation-Only Validation (0% Hardware): Scripted Gazebo actors lack human micro-accelerations and optical motion blur/glare. Quantified impact on specification: Real-world frustum association would likely drop by 5–8% from the simulated Target (≥ 95%), justifying our conservative Minimum threshold of ≥ 85% (O1-b) and seeded speed/angle randomization.

•  Planar Intersection Height & 80° Camera FOV: Metric depth requires targets to intersect the 10–20 cm laser plane within the camera's 80° horizontal FOV. Quantified impact: Agents outside the 80° camera frustum cannot be velocity-tracked until entering the FOV; outside this zone, the system defaults to the 360° static 2D LiDAR costmap (C0), preserving the 0-collision constraint (O2-c).

•  Constant-Velocity Horizon Divergence (T > 2.0 s): Under a sudden pedestrian direction reversal (a ≈ 1.5 m/s²), linear CV position error grows quadratically as Δp = ½aτ², reaching 0.38 m at τ = 1.0 s and 1.50 m at τ = 2.0 s. Quantified impact: Preview is strictly bounded to T = 2.0 s with linear uncertainty inflation σ_i(τ_k) = R_rob + R_obs + α·τ_k, trading long-range swerving for guaranteed stability on O1-a (< 0.15 m/s) and O2-c (0 collisions).

# 5. Risk Management

Project management and technical delivery risks (excluding generic laboratory health and safety) are quantified using Likelihood (L ∈ [1, 5]) and Impact (I ∈ [1, 5]), sorted by composite score S = L × I and quantified schedule/specification impact (Table 7). Risks scoring S ≥ 15 are classified as Critical (R2, R1, R3), rated pre- and post-mitigation, and linked to scheduled review gates and technical fallbacks.

Table 7. Quantified project risk register sorted by risk score and impact, showing pre- and post-mitigation ratings (L × I).

| ID | Risk Description & Methodology Link | When | L | I | Pre | Quantified Unmitigated Impact | Realistic Mitigation Strategy & Fallback Action | Post |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R2 | Custom C++ MPPI critic plugin (M3) suffers compilation, memory, or latency faults | W8 spike; W13–W18 | 4 | 5 | 20 (Crit) | 3–4 wks slip; threatens O2 delivery | Execute early 'Hello-Critic' C++ pluginlib spike in W8. Fallback F1: Implement VelocityInflationLayer costmap plugin projecting anisotropic ellipses into nav2_costmap_2d, preserving O2-a/b/c. | 9 (3×3) |
| R1 | Host OS, ROS 2 Jazzy, Gazebo Harmonic, or GPU driver drift breaks pipeline (M0) | W1–W3 | 4 | 4 | 16 (Crit) | 2–3 wks slip at project start | Dedicate W1 to host benchmarking (Ubuntu 24.04 dual-boot vs. WSL2); lock ROS 2 + Gazebo + boxmot stack in a pinned Docker image (NF1). | 6 (2×3) |
| R3 | Scope creep across tracker, critic, and 450-run ablation exceeds 450 h budget (M2–M5) | All phases (R1–R5) | 4 | 4 | 16 (Crit) | 3–6 wks slip; incomplete stats | Commit strictly to simulation scope (SD-MEng-26-01); gate Stretch Goals S1–S3 behind Review 3 (W18); shed 4-agent crowd runs first if behind. | 9 (3×3) |
| R4 | Extrinsic calibration error or laser wall bleed-through corrupts KF velocity (M2) | W7–W12 | 3 | 4 | 12 | 2 wks slip; O1-a > 0.25 m/s | Use exact simulator TF extrinsics first; apply frustum median depth clustering and Chi-square Mahalanobis gating (d_M^2 < γ) to reject wall hits. | 6 (2×3) |
| R7 | Competing MEng coursework and Jan/Apr exam periods reduce weekly FYP hours | W10–W14; W23–W26 | 4 | 3 | 12 | 2–3 wks slip in exam windows | Schedule lighter FYP loads (8–10 h/wk) during exam weeks offset by 18 h/wk in Nov/Feb; preserve an unallocated 15-hour buffer in Week 30. | 6 (3×2) |
| R5 | Multi-actor visual occlusions in Scenario D cause track ID switches (M2) | W9–W14 | 3 | 3 | 9 | 1–2 wks slip; O1-b < 85% | Use ByteTrack [8] two-stage low-score box association (θ_low = 0.1); enforce 1.0 s coasting timeout and covariance reset upon re-identification. | 4 (2×2) |
| R6 | Deterministic Gazebo actor motion causes controller overfitting (M1, M4) | W19–W24 | 4 | 2 | 8 | Spec change: weaker O3 claims | Inject seeded uniform random perturbations into actor spawn times, speeds (0.5–2.0 m/s), and crossing angles across all 30 paired trials. | 6 (3×2) |
| R8 | Source code corruption or loss of raw rosbag2 ablation datasets (All) | All phases | 2 | 4 | 8 | 1–2 wks lost re-running trials | Git repository with remote GitHub backup, weekly semantic tags at milestones, and automated cloud sync of compressed CSV summary logs. | 4 (1×4) |
| R9 | Aspirational Target hypotheses (0 freezes in O2-a) missed in dense traffic | W19–W24 | 3 | 2 | 6 | Spec change: Target missed | Two-tier specification (Minimum vs. Target) guarantees baseline pass (≥ 50% freeze reduction) while reporting exact failure boundaries. | 4 (2×2) |

# 6. Planned Work Schedule

The project spans 30 weeks from Week 1 (12 October 2026) to Week 30 (9 May 2027) at a realistic nominal workload of 15 hours per week, totaling 450 hours (Table 8). Every task embeds an explicit Develop (60%) – Test (25%) – Document (15%) cycle and concludes at one of five supervisor Progress Reviews (R1–R5).

Table 8. Phased work breakdown, task hours (Develop/Test/Doc split), links to spec/methodology, uncertainty, and review expectations.

| Phase & Weeks | Major Tasks, Spec/Method Links & Hour Split (Dev/Test/Doc) | Hours | Uncertainty & Impact | Progress Review Milestone & Expected Status |
| --- | --- | --- | --- | --- |
| Phase A: Foundations W1–W6 (12 Oct–22 Nov) | • T0 (M0, NF1): Host Ubuntu 24.04 + ROS 2 Jazzy + Docker (50h: 30D/12T/8Doc) • T1 (M1, C0): Gazebo corridor world, actors & C0 baseline (40h: 24D/10T/6Doc) | 90 h (15 h/wk) | ±1 wk on T0/T1. Absorbed pre-R1. | Review 1 (W6, ≈ 16 Nov 2026): Docker frozen (NF1); Gazebo world ready; C0 baseline freezes measured on Scenarios A–E. |
| Phase B: Tracker W7–W12 (23 Nov–3 Jan) | • T2 (M2, O1-a/b): YOLOv8n + ByteTrack + Frustum gate + KF (75h: 45D/19T/11Doc) • T3a (M4, O3): Scenario spawner & W8 C++ critic spike (15h: 9D/4T/2Doc) | 90 h (15 h/wk) | ±2 wks on T2. W8 spike decides R2 critic vs. F1. | Review 2 (W12, ≈ 28 Dec 2026): /tracked_obstacles at ≥ 30 Hz; O1-a RMSE (< 0.25 m/s) & O1-b (≥ 85%) met; W8 spike passed. |
| Phase C: Critic W13–W18 (4 Jan–14 Feb) | • T4 (M3, O2-a/b/c): DynamicObstaclesCritic C++ plugin (75h: 45D/19T/11Doc) • T3b (M4, O3): Batch rosbag2 evaluator & C1 config (15h: 9D/4T/2Doc) | 90 h (15 h/wk; Jan exams) | ±3 wks on T4. If slipped > W16, trigger Fallback F1. | Review 3 (W18, ≈ 8 Feb 2027): C2 dynamic critic & C1 running closed-loop at ≥ 20 Hz (O3-c) with 0 collisions; S1–S3 gate. |
| Phase D: Ablation W19–W24 (15 Feb–28 Mar) | • T3c (M4, O3-a/b/c): Batch 3-way ablation (450 trials) (55h: 30D/17T/8Doc) • T5a (M5, O3-a): Paired Welch t-test, ANOVA & profiling (35h: 20D/9T/6Doc) | 90 h (15 h/wk) | ±2 wks on T3c. Reallocate T5b stretch hours. | Review 4 (W24, ≈ 22 Mar 2027): All 450 paired runs complete; statistical separation (p < 0.05) verified (O3-a); draft tables done. |
| Phase E: Thesis W25–W29 (29 Mar–2 May) | • T5b (M5, S1–S3): Sensitivity plots & stretch benchmarks (30h: 15D/8T/7Doc) • T7a (Core): MEng thesis drafting & video demos (45h: 0D/10T/35Doc) | 75 h (15 h/wk; Apr exams) | ±1 wk on T5b. Protected by W30 buffer. | Review 5 (W29, ≈ 26 Apr 2027): Complete thesis draft reviewed with supervisor; demo videos rendered; NF1 container verified. |
| Close & Buffer W30 (3 May–9 May) | • T7b (Core): Final thesis proofreading, formatting & submission buffer (15h: 0D/3T/12Doc) | 15 h (15 h/wk) | 15 h reserve absorbs slip. | Final Submission (W30, ≈ 7 May 2027): Final dissertation, code, and videos submitted. |

Figure 3. Project Gantt chart showing Develop–Test–Document cycles, parallel stream T3a–b, uncertainty error bars (+1 to +3 wks), exam windows, and Progress Reviews R1–R5.

Dependencies, Parallelisation, and Uncertainty Absorption: The critical path runs along T0 → T1 → T2 → T4 → T3c → T5a → T7a. Running the scenario and logging harness (T3a–b) in parallel during Weeks 8–18 ensures batch testing (T3c) starts immediately after R3. Schedule uncertainty is concentrated in T2 (+2 wks), T4 (+3 wks), and T3c (+2 wks): if T2 slips, T4 development proceeds in parallel using synthetic Gazebo ground-truth /tracked_obstacles messages; if T4 slips into Phase D, T5b (30 h stretch analysis) and the Week 30 buffer (T7b, 15 h) absorb the overrun without dropping core objectives O1–O3.

# References

[1] International Federation of Robotics (IFR), "World Robotics 2025 – Service Robots," Frankfurt, Germany, Press Release, 2025. [Online]. Available: https://ifr.org/ifr-press-releases/news/service-robots-see-global-growth-boom

[2] S. Macenski, F. Martín, R. White, and J. Ginés Clavero, "The Marathon 2: A Navigation System," in Proc. IEEE/RSJ Int. Conf. Intelligent Robots and Systems (IROS), Las Vegas, NV, USA, 2020, pp. 2718–2725, arXiv:2003.00368.

[3] S. Macenski, T. Foote, B. Gerkey, C. Lalancette, and W. Woodall, "From the Desks of ROS Maintainers: A Survey of Modern & Capable Mobile Robotics Algorithms in the Robot Operating System 2," Robotics and Autonomous Systems, vol. 168, p. 104496, 2023, arXiv:2307.15236.

[4] P. Trautman and A. Krause, "Unfreezing the robot: Navigation in dense, interacting crowds," in Proc. IEEE/RSJ Int. Conf. Intelligent Robots and Systems (IROS), Taipei, Taiwan, 2010, pp. 797–803, doi:10.1109/IROS.2010.5654369.

[5] G. Williams, N. Wagener, B. Goldfain, P. Drews, J. M. Rehg, B. Boots, and E. A. Theodorou, "Information theoretic MPC for model-based reinforcement learning," in Proc. IEEE Int. Conf. Robotics and Automation (ICRA), Singapore, 2017, pp. 1714–1721, doi:10.1109/ICRA.2017.7989202.

[6] Q. Zhang and R. Pless, "Extrinsic calibration of a camera and laser range finder (improves camera calibration)," in Proc. IEEE/RSJ Int. Conf. Intelligent Robots and Systems (IROS), Sendai, Japan, 2004, pp. 2301–2306, doi:10.1109/IROS.2004.1389752.

[7] S. Thrun, W. Burgard, and D. Fox, Probabilistic Robotics. Cambridge, MA, USA: MIT Press, 2005.

[8] Y. Zhang, P. Sun, Y. Jiang, D. Yu, F. Weng, Z. Yuan, P. Luo, W. Liu, and X. Wang, "ByteTrack: Multi-Object Tracking by Associating Every Detection Box," in Proc. European Conf. Computer Vision (ECCV), Tel Aviv, Israel, 2022, pp. 1–21, arXiv:2110.06864.

[9] D. Helbing and P. Molnár, "Social force model for pedestrian dynamics," Physical Review E, vol. 51, no. 5, pp. 4282–4286, 1995, doi:10.1103/PhysRevE.51.4282.

[10] S. Macenski and Nav2 Development Team, "Nav2 MPPI Controller: Model Predictive Path Integral Trajectory Optimization," ROS 2 Navigation Stack Documentation, 2024. [Online]. Available: https://github.com/ros-navigation/navigation2/tree/main/nav2_mppi_controller

[11] J. M. Kang, "SE-MPPI: Safe-Escape Nav2-Native MPPI Controller with Control Barrier Functions," GitHub Repository / Technical Preprint, 2024. [Online]. Available: https://github.com/kjungmo/se-mppi-nav2

[12] C. Peng et al., "EXACT-MPPI: Exact Signed-Distance Navigation for Arbitrary-Footprint Robots from Point Clouds via Path Integral Control," Technical Preprint / GitHub Repository, 2024. [Online]. Available: https://github.com/caseypen/EXACT-mppi

[13] Robot Control and Intelligence Lab (RCILab), "Constrained Sampling MPPI Framework with DBSCAN for Reliable Obstacle Avoidance," in Proc. IEEE/RSJ Int. Conf. Intelligent Robots and Systems (IROS), 2025.

# Appendix A: Supervisor-Provided Project Specification

Project Title: Vision-Augmented Mobile Robot Navigation in Dynamic Environments
Project Code: SD-MEng-26-01   |   Supervisor: Dr Shalini Darmaraju   |   Moderator: Ir Dr Daniel Pu   |   Date: 19 October 2026

## A.1 Project Description

Autonomous mobile robots need to navigate safely and efficiently in environments containing moving obstacles. Planar range sensors provide distance measurements, while cameras provide visual information that can help identify relevant obstacles. Combining these inputs with obstacle motion estimation can support navigation decisions when obstacles cross or approach the robot’s planned route.

This project aims to develop a simulation-based navigation framework that combines camera information with planar range measurements for obstacle tracking and motion-aware navigation. A mobile robot equipped with simulated sensors will operate in a known indoor environment containing selected types of moving obstacles. Existing visual detection and tracking methods will be adapted and combined with range measurements to estimate obstacle positions and velocities. A simple motion model will predict their short-term positions, which will be incorporated into local path planning and collision avoidance using an existing navigation framework.

The proposed system will be evaluated against range-sensor-based navigation, with additional comparisons to distinguish the effects of visual information and motion prediction. Experiments will vary obstacle speeds, movement patterns and density. Evaluation will assess tracking accuracy, navigation success, collisions, travel time, waiting time and computational efficiency. All development and evaluation will be conducted in simulation, with images and range measurements generated by simulated sensors.

## A.2 Target Sustainable Development Goals (SDGs)

•  SDG 9: Industry, Innovation and Infrastructure

•  SDG 8: Decent Work and Economic Growth

## A.3 Project Objectives

•  1. To review existing methods for vision-augmented mobile robot navigation, camera and range-sensor integration, obstacle tracking and motion prediction.

•  2. To develop an indoor robot simulation and adapt existing detection and tracking methods to combine simulated camera and planar range measurements for obstacle position and velocity estimation.

•  3. To develop a navigation framework that incorporates short-term obstacle motion predictions into local path planning and collision avoidance.

•  4. To evaluate the proposed framework against range-sensor-based navigation under varying obstacle movements and densities, assessing tracking accuracy, navigation performance and computational efficiency.

## A.4 Project Deliverables & Resource Breakdown

•  1. A literature review of vision-augmented mobile robot navigation, camera and range-sensor integration, obstacle tracking and motion prediction methods.

•  2. A configurable indoor robot simulation and an implemented obstacle detection and tracking system using simulated camera and range measurements, with documented source code.

•  3. A navigation prototype integrating short-term obstacle motion prediction with local path planning and collision avoidance.

•  4. Comparative experimental results and analysis of tracking accuracy, navigation success, collisions, travel time, waiting time and computation time, supported by reproducible simulation scenarios and video demonstrations.

•  5. A final project report documenting the literature review, methodology, system development, evaluation results and conclusions.

Resource Ratio: Hardware 0% | Software 60% | Research/Investigation/Design 40%. Facilities: Computer workstation only (Ubuntu Linux, ROS 2, Nav2, Gazebo, Python/C++, NumPy, Matplotlib).